BIL 481 – Software Engineering

Project Plan Document

PA1 – Part 1

Project: PawSafe – Stray Dog Location Reporting System

Contributors:

Yusuf Yankı Ütgün

Eren Can Dönertaş

Yiğit Eren Yılmaz

Enes Kerem Göksu

Table of Contents

1. Project Scope

2. Project Organization

3. Objectives

4. Key Phases and Timeline

5. Resource Planning

6. Risk Management

7. Communication Plan

8. Change Management Plan

9. Budget Plan

10. Effort Estimation

11. Task Matrix

12. Rationale for Task Assignment

1. Project Scope

PawSafe will be a mobile application built with Flutter and Firebase. The system includes user authentication, GPS-based dog location reporting, a live map view, time-based filtering, an admin panel, and basic analytics. All four team members will contribute to all phases of the project. Out of scope: government integrations, AI animal detection, social features, desktop app, in-app payments.

2. Project Organization

All team members will participate in both frontend and backend development. The roles below reflect each member's primary area of focus, not exclusive ownership. Every feature will be developed, reviewed, and tested collaboratively.

| Member | Primary Focus | Responsibilities |
| --- | --- | --- |
| Yusuf Yankı Ütgün | Project Manager / Full-Stack | Coordination, sprint planning, GitHub management, contributes to both frontend and backend implementation across all phases. |
| Eren Can Dönertaş | Frontend (Flutter) | Leads Flutter UI implementation. Also contributes to backend integration and testing. |
| Yiğit Eren Yılmaz | Backend (Firebase) | Leads Firebase setup and Cloud Functions. Also contributes to Flutter screens and testing. |
| Enes Kerem Göksu | UI/UX / Full-Stack | Leads Figma wireframes and admin panel. Also contributes to Flutter screens, backend, and testing. |

3. Objectives

- Submit all PA1 documents to GitHub by February 5, 2026.

- Submit the Design Document (PA2) to GitHub by February 12, 2026.

- Complete all application features and pass testing by April 10, 2026.

- Maintain clear individual contributions from all four members on GitHub throughout the project.

4. Key Phases and Timeline

| Phase | Description | Start | End | All Members Involved |
| --- | --- | --- | --- | --- |
| Phase 1 – Documentation | PA1 documents: Project Definition, Plan, Requirements, Backlog. | Feb 1 | Feb 5, 2026 | Yes |
| Phase 2 – Design | PA2 Design Document. UI wireframes, architecture, tech stack. | Feb 5 | Feb 12, 2026 | Yes |
| Phase 3 – Setup | Firebase project, Flutter scaffold, GitHub structure, Figma design system. | Feb 12 | Feb 19, 2026 | Yes |
| Phase 4 – Dev Sprint 1 | User authentication (register, login, reset). Basic map screen. | Feb 19 | Mar 5, 2026 | Yes |
| Phase 5 – Dev Sprint 2 | Report submission, live map markers, time filtering, admin panel. | Mar 5 | Mar 26, 2026 | Yes |
| Phase 6 – Dev Sprint 3 | Push notifications, analytics screen, marker clustering, performance. | Mar 26 | Apr 7, 2026 | Yes |
| Phase 7 – Testing & Final | Test case execution, bug fixes, demo preparation. | Apr 7 | Apr 10, 2026 | Yes |

5. Resource Planning

| Resource | Tool/Service | How Accessed |
| --- | --- | --- |
| Frontend Framework | Flutter SDK | flutter.dev – installed locally on each device |
| Backend & Auth | Firebase | console.firebase.google.com – shared team project |
| Database | Cloud Firestore | Part of Firebase project |
| Maps | Google Maps API | Google Cloud Console – API key in project config |
| Design | Figma | figma.com – shared team workspace |
| Version Control | GitHub | Shared repository – each member has own account |
| Communication | WhatsApp + Google Meet | Team group chat + weekly video calls |

6. Risk Management

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Team member unavailability | Medium | High | All work is documented and committed to GitHub so others can continue. |
| Scope creep / extra features | Medium | High | New features need full team agreement before adding. |
| Firebase quota exceeded | Low | Medium | Monitor Firebase console; optimize queries. |
| GPS inaccuracy | Medium | High | High-accuracy mode; allow manual pin adjustment. |
| Timeline delays | Medium | High | Weekly check-ins; adjust sprint scope if needed. |

7. Communication Plan

| Channel | Frequency | Purpose |
| --- | --- | --- |
| WhatsApp Group | Daily | Quick updates, questions, file sharing. |
| Google Meet | Weekly (Mondays) | Sprint review, planning, blocking issues. |
| GitHub Issues / PRs | Per task | Code review, task tracking, bug reports. |

Stakeholder (instructor) communication: via GitHub repository submissions and course portal per announced deadlines.

8. Change Management Plan

- Any team member identifies a potential change and raises it in the WhatsApp group.

- The change is discussed at the next weekly meeting.

- If accepted by the full team, the Project Manager updates the affected documents and

GitHub backlog.

- Changes that affect submitted deliverables must be documented in the repository.

9. Budget Plan

| Phase | Est. Total Hours | Cost |
| --- | --- | --- |
| Phase 1 – Documentation | 32 | $0 |
| Phase 2 – Design | 24 | $0 |
| Phase 3 – Setup | 16 | $0 |
| Phase 4 – Dev Sprint 1 | 48 | $0 |
| Phase 5 – Dev Sprint 2 | 64 | $0 |
| Phase 6 – Dev Sprint 3 | 48 | $0 |
| Phase 7 – Testing & Final | 24 | $0 |
| TOTAL | 256 | $0 |

All tools and services are within free tiers. No hardware purchases required.

10. Effort Estimation per Phase

Estimation method: Expert Judgment based on team discussion. All four members contribute equally to each phase. Hours per member are balanced to reflect shared ownership of the project.

| Phase (hours) | Yusuf Y. Ütgün | Eren C. Dönertaş | Yiğit E. Yılmaz | Enes K. Göksu | Total |
| --- | --- | --- | --- | --- | --- |
| Phase 1 – Documentation | 8 | 8 | 8 | 8 | 32 |
| Phase 2 – Design | 6 | 6 | 6 | 6 | 24 |
| Phase 3 – Setup | 4 | 4 | 4 | 4 | 16 |
| Phase 4 – Dev Sprint 1 | 12 | 12 | 12 | 12 | 48 |
| Phase 5 – Dev Sprint 2 | 16 | 16 | 16 | 16 | 64 |
| Phase 6 – Dev Sprint 3 | 12 | 12 | 12 | 12 | 48 |
| Phase 7 – Testing & Final | 6 | 6 | 6 | 6 | 24 |
| TOTAL | 64 | 64 | 64 | 64 | 256 |

11. Task Matrix

All members contribute to every phase. The table shows primary responsibility per phase, but all members actively participate in implementation, review, and testing.

| Phase / Task | Yiğit Eren Yılmaz | Eren Can Dönertaş | Yusuf Yankı Ütgün | Enes Kerem Göksu |
| --- | --- | --- | --- | --- |
| Phase 1 – Documentation | Project Plan | Requirements Doc | Requirements Doc | Project Definition |
| Phase 2 – Design | Architecture | Use Case Design | Data Schema | Wireframes |
| Phase 3 – Setup | GitHub / CI Setup | Flutter Scaffold | Firebase Setup | Figma Design System |
| Phase 4 – Dev Sprint 1 | Auth Backend + UI | Auth UI Screens | Auth Backend | Login/Register Design |
| Phase 5 – Dev Sprint 2 | Map Backend | Map UI + Filter | Firestore Rules | Admin Panel |
| Phase 6 – Dev Sprint 3 | Notifications Backend | Analytics UI | Push Notif. Backend | Analytics Design |
| Phase 7 – Testing & Final | Test Execution | Bug Fixes | Bug Fixes | Demo Prep |

12. Rationale for Task Assignment

The team agreed from the start that all members would be involved in all phases of the project, both frontend and backend. Roles reflect each member's primary area of focus, not exclusive ownership. This approach ensures that:

- No single member becomes a bottleneck. If one person is unavailable, others can continue.

- All members gain experience across the full stack.

- Effort is distributed evenly: each member contributes 64 hours across the project (25% each).

- GitHub commit history will reflect contributions from all four members in every major phase.

Task Matrix – Project Plan Document

All members contributed to every section of this document through joint discussion and review sessions.

| Task | Yiğit | Eren C. | Yusuf | Enes |
| --- | --- | --- | --- | --- |
| Scope | Author | Review | Review | Review |
| Organization Table | Author | Review | Review | Review |
| Timeline | Review | Author | Review | Review |
| Resource Plan | Review | Review | Author | Review |
| Risk Management | Review | Review | Review | Author |
| Communication Plan | Author | Review | Review | Review |
| Change Management | Review | Author | Review | Review |
| Budget & Effort | Review | Review | Author | Review |
| Task Matrix + Rationale | Review | Review | Review | Author |
| GitHub Upload | Author | Review | Review | Review |